## Sheet1
ZEIT3506 Programme
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Break | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
| Course Intro | Pre-Acquisition | Project initiation & Concept. Design | Concept Design - Requirements Focus | Prelim. Design - Analysis focus | Prelim. Design- Cost focus | Prelim. Design- Risk focus |  | Prelim Design- Quality focus | Detailed Design - procurement | Monitoring & Alternative Approaches | Construction | Utilisation & Sustainment | Course Summary
PM | What is a project |  | PM initiation processes | Create WBS initial | Define activites | Plan cost management | Plan risk management |  | Plan resource management | Detailed Schedule | Earned Value mgt | Acquire resources | Validate scope | Project charter
| What is PM | Evaluating project portfolios | Develop project management plan | Plan Schedule management | Sequence activities | Estimate costs- analogous, parametric, bottom up | Identify risks and risk analysis |  |  | CPM, levelling, crashing etc | progress reporting | Develop team | Control scope | Stakeholder analysis
| Common failures | Business case | Plan and define Porject scope | Rolling wave planning | Estimate Activity durations | Determine budget | Plan risk responses |  | Plan Stakeholders engagement |  | Updating schedule and cost estimate | Manage team | Control schedule | Project management plan
| PMBOK overview | Develop Project Charter | Collect Requirements | Work distribution model | Develop high-level Schedule |  |  |  | Service quality | PERT | Issue management | Implement risk response | Control costs | WBS
| Organisational context | Identify stakeholders | [6 empty] | Cost of rework | Plan procurement management |  | Conduct procurements | Control resources | Schedule-CPM, levelling
| What is an effective PM org | stakeholder analysis | [11 empty] | Earned value management
| What is a methodology | [12 empty] | Risk analysis
| When in system lifecycle does a project occur | [12 empty] | Control projects
SE | What is a system | CONOPS | Use cases | Sys Req Spec | Synthesis of design | Other SE tools/models | Tec risk management |  | Preliminary design review |  | Critical design review | T&E plan | Operation incident reporting
| What is SE | Primary use cases | System context | Good requ statements | design excellence |  |  |  | Sub Sys Spec and Design Document |  | Alternative approaches | Design for manufacturability | Config management
| System Lifecycle | Intro to lifecycle concepts | System scope | Traceability | diverge/convergent thinking |  |  |  | T&E plan |  | Agile | Production FMEA | Fleet management
| Introduce Innosolate |  | Critical Op issues | System architecture | Class diagrams |  | Tech perf measures |  |  | Product spec | Evolutionary etc |  | Engineering change process
|  |  | high level FFBDs | Sys design review | modularity |  | Ishikawa diagram/ root cause analysis
[5 empty] | subsys boundaries |  | FMEA
Sus | What is a capability | Lifecycle costing models | LCC trade studies | Maintainability and maintenance approaches eg predictive | reliability/availability statistics | Repairable Systems Reliability | Software Reliability |  | Quality Definitions, Dimensions and Philosophers | Quality Improvement Tools |  | Design Verification and Validation | Industry Speakers | Student Case study presentation and discussions
| Organisational context | Sustainment concepts | System availability/reliability requirements | Maintenance Planning and Materials Management | FTA |  | Asset Management |  | Six Sigma | Root cause analysis |  |  | What is sustainment
| Product lifecycle management |  | Asset Lifecycle & Lifecycle Cost Management | Maintenance Planning and Scheduling | Failure Rate Concept | Failure Data Analysis | Reliability Management and Related Decision Making |  | DMAIC (Design, Measure, Analyze, Improve, Control) | Idea Diagrams: cause and effect, affinity and tree diagrams | Experiments | Design for manufaturability | Configuration mgt
| Product manager role | HUMS feedback/lessons learnt |  | Predictive Maintenance Strategy | Why-because analysis | Parameter Estimation | LORA |  | rolled throughput yield | Bill of materials mgt - alternative suppliers etc | Robust Design |  | HUMS feedback/lessons learnt
| extended enterprise. | tech. reg. framework |  |  | Failure rate profiles Weibull dist |  |  |  |  | improvement project planning: SIPOC diagram |  |  | tech. reg. framework
lecture theme | Systematic development of a new capability | Development process is business driven - initiated by business | Manage the development process. Top-down requirements systematic requirements analysis | Proper functional requirements collected in SyRS - functional baseline | Entering the solution domain - allocation of rqmnts - synthesis of design | Progressive ellaboration of costs and schedule | Risk management - project and tech risks |  | Allocated baseline formally review at PDR | Fully in solution space, design decisions, T&E design | Waterfall is not the only approach. Development must be controlled. | Manufacturability must be feed into the design | Operations and sustainment requirements must be feed into the design
At home | Read scenario | Develop charter | Lower level use case | Create initial WBS | [5 empty] | Example design descision
| Read Chaos report | Learn Innosolate | FFBD | Produce requirements statements in Innosolate | lower level FFBD
| Read PMBOK lead in | Look up tech reg framework for the scenario | Context diagram/system boundary |  | subsystem context/boundary
| Read se lead in | Identify stakholders | Describe LC trade-off issue |  | class diagram
| Sign-on Innosolate, learn basics |  | Develop scope statements (inclusions, exclusions, constraints and assumptions)
Load MS Project, learn basics
Tutorial | Introduce scenario | Review charter | Review homework | Requirements statements in RBS | Review homework |  |  |  |  | Design decisions
| Organisational structures and jobs | Review tech reg framwork | Use Innosolate for artifacts |  | lower level FFBD
| Issues with different org structures | Stakeholder analysis | Work through a trade-off |  | Lower level use cases
| PM job | Sustainment concepts | Develop PMP
| SE job | Rich picture | Scope statements
| Contract the "equipment" with the "capability" |  | Early schedule (MS Project)
Resources | Company org structure | Scenario tech reg framework | Scope statements | Requirements statements in RBS | WBS dictionary | MS Project - resourcing and budget | Risk matrix |  | SSRS SSDD | PMP procurement section | EVM examples | Production FMEA | Failure report example
| MS Project tutorial reference | Stakeholder matrix | Trade off example | WBS | Subsystem context diagram - internal interfaces | PMP resource mgt section | TPMs |  | T&E plan (SEMP?) | Example - procurement pack (SOW, specs, T&Cs) | Alternative dev plan for SW element |  | ECR/ECN
|  | Rich picture | PMP | Maintenance concept incl use case | Interface control doc |  | FMEA |  | PMP quality section | CPM examples incl MS Project | Agile use stories, backlog etc |  | Tech reg framework
|  | Charter | system context diagram |  | Availability/reliability analysis |  | Root cause diagram |  |  | product spec |  |  | User feedback
|  |  | Lower level use case | [6 empty] | BOM example/tech drawinf

## Summary
Course design plan for ZEIT3506-System Engineering & Management (S2, 2019) | [13 empty] | Version: 29/05/2020
Items | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Break | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Topic/Theme | Course Introduction | Pre-Acquisition | Project initiation & Conceptual Design | Conceptual Design - Requirements Focus | Preliminary Design - Analysis focus | Preliminary Design- Cost focus | Preliminary Design- Risk focus |  | Preliminary Design- Quality, testing and review focus | Detailed Design and scheduling focus | Control, Monitoring & Alternative Approaches | Construction & procurement | Utilisation & Sustainment | Course Summary
Learning outcomes (number only) | LO1-LO3 | LO1-LO3 | LO1-LO3, LO5 | LO1-LO3, LO5 | LO1-LO3, LO5 | LO1-LO5 | LO1-LO3 |  | LO1-LO3, LO5 | LO1-LO4 | LO1-LO5 | LO1-LO5 | LO1-LO5 | LO1-LO5
Activity (Purpose) | Discuss about course admin. Introduce with tutors/lecturers. Explain the systematic development of a new capability ( 3 inter-related disciplines) | Articulate that the development is business driven - initiated by business. Guide students for the group formation for their group assignments. Open for online discussion, while interactions should be peer to peer (for group work) | Explain how to manage procecesses and do the systematic requirement analysis. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Articulate how to collect proper functional requirements in SyRS (functional baseline). Coordinate 1st Online Quiz. | Entering the solution domain - allocation of requirements - synthesis of design including availability and reliability requirements. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | As the design progresses, explain how there is progressive ellaboration of costs and schedule and also how to manage them. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Articulate how to manage both project and technical risks. Interactive vedio lecture and online discussion among peer to peer and with the lecturer. |  | Explain how to manage both product (technical) & service quality. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Coherently demonstrate how to handle detailed design decisions and T&E design, which should lead to a detailed schedule. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Narrate the agile user stories for the Customer System Manager application. Coordinate the 2nd Online Quiz | Explain how to draw a 'Design for manufacture' toolbox, which should be feed for the procurement process. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Articulate how to prepare an operations and sustainment requirements plan, which must be feed into the design. Interactive vedio lecture and online discussion among peer to peer and with the lecturer | Review whole course materials. Interactive vedio lecture and online discussion with the lecturer
Student study time | 6 | 6 | 6 | 20 | 6 | 7 | 20 |  | 8 | 10 | 20 | 6 | 20 | 15
Moodle Tools | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats | Quiz and online chats | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats |  | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats | Quiz and online chats | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats | Reflective Journal (Discusson Forum) and online chats
Resources | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); MOOC Videos | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); MOOC Videos | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); MOOC Videos | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); Microsoft Project | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); MOOC Videos | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); Microsoft Project | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle) |  | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle) | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); Microsoft Project | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle); Microsoft Project | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle) | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle) | Course reading materials in Lenganto (link in Moodle); MindTap resources (link in Moodle)
Facilitation tasks (teaching presence) | Ripon will explain the course administration process, Ripon will explain how to install Microsoft Visio and Microsoft Project, Matt will introduce the course and explain how theree different disciplines are interrelated | Ripon will post welcome message to students. Ripon will reinforce the need of posting in the Reflective Journals, Q&A forum, and participate in online discussions. All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will cross-check online quiz marks and will provide feedback or clarifications. They will provide sample answers during the tutorial sessions. | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will cross-check group assignment submissions and will provide feedbacks or clarifications. They will provide sample answers during the tutorial sessions. |  | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will cross-check online quiz marks and will provide feedback or clarifications. They will provide sample answers during the tutorial sessions. | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks | All five lecturers will cross-check group assignment submissions and will provide feedbacks or clarifications. They will provide sample answers during the tutorial sessions. | All five lecturers will reply to student's enquires posted in the Reflective Journal or Q&A forum. They will invite student's to share their progress about the group works and will give formative feedbacks
Assessment type (% of final mark) | None | Formative (Online engagement, e.g., Reflective Journal): 1% | Formative (Online engagement, e.g., Reflective Journal): 1% | Summative (Online Quiz): 15% | Formative (Online engagement, e.g., Reflective Journal): 2% | Summative (Group Assignment/process): 15% | Formative (Online engagement, e.g., Reflective Journal): 2% |  | Formative (Online engagement, e.g., Reflective Journal): 1% | Formative (Online engagement, e.g., Reflective Journal): 2% | Summative (Online Quiz): 15% | Formative (Online engagement, e.g., Reflective Journal): 1% | Summative (Group Assignment/process): 15% | None
Feedback | Online comments and responses in Reflective Journal (Discussion page): formative | Online comments and responses in Reflective Journal (Discussion page): formative | Online comments and responses in Reflective Journal (Discussion page): formative | Automated feedback: Summative | Online comments and responses in Reflective Journal (Discussion page): formative | Online comments and responses in Reflective Journal (Discussion page): formative | Responses on group assignments (both online and offline): Summative |  | Online comments and responses in Reflective Journal (Discussion page): formative | Online comments and responses in Reflective Journal (Discussion page): formative | Automated feedback: Summative | Online comments and responses in Reflective Journal (Discussion page): formative | Responses on group assignments (both online and offline): Summative | Online comments and responses in Reflective Journal (Discussion page): formative
Student Support | Moodle user guide, Q& A Forum (in Moodle), Announcements Tab (in Moodle), Library and ICTS (for installing Microsoft Project) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) |  | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle) | Q& A Forum (in Moodle), Announcements Tab (in Moodle)
Learning Outcomes | LO1. Explain how the project management discipline applies to a medium-complexity engineering development project; LO2. Explain how the systems engineering discipline applies to a medium-complexity engineering development project; LO3. Explain how the capability sustainment discipline applies to a medium-complexity engineering development project; LO4. Develop a project management plan integrating the disciplines of project management, systems engineering and capability sustainment; LO5. Specify system requirements by analysing capability needs using key SE techniques and tools.